## Cover
TEST PLAN
Project Name | Test Website CellphoneS |  |  | Reviewer | Team
Project Code |  |  |  | Review date
Creator | Group 13 |  |  | Approver
Version | v1.0 |  |  | Approval Date
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-01-02 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Detail Schedule
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
SRS_Group13 |  |  |  | v1.0

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
# | Description | Responsibility | Note
1
2
Test case design policy
Description of policies of test case design.
# | Items | Note
1
2
Quality metric
Description of target
# | Items | Target | Note
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
# | Criteria | Priority | Note
1 | 80% of completed test cases / total test cases (test coverage > 80%) |  | Carry out test cases with highest priority first, then increase gradually.
2 | Test successful coverage >= 80%
3 | Software is correct with SRS
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
# | Suspension Criteria | Note
1 | When a defect is introduced that cannot allow any further testing
2 | A specific holiday shuts down both development and testing (Tet Holiday)
3 | If there is any network, hardware problem in the organisation, we can suspend testing
4 | If we got more pending requests with the development team
# | Resumption Requirements | Note
1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Tạo test plan |  |  | Leader / Team
2 | Tạo test design |  |  | Team
3 | Tạo test cases |  |  | Team
4 | Tạo test data |  |  | Team
5 | Thực thi system test |  |  | Team
6 | Defects list |  |  | Team
7 | Tạo test report |  |  | Team
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2023-11-27 | Team | Test manager, Team | This document itself
2 | Test cases | 2023-11-27 | Team | Test manager, Team
3 | Defect logs | 2023-11-27 | Team | Test manager, Team
4 | Test report | 2023-11-27 | Team | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on F32: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on H32: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on C41: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
Tất cả các chức năng của hệ thống CellphoneS được mô tả trong tài liệu SRS, các chức năng được kiểm tra theo thứ tự ưu tiên từ cao đến thấp (ưu tiên cao nhất được kiểm tra trước) |  | SRS_Group13_v1.0
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Smartphone
OS | Window 10 64bit Android 13.0
Software | Chrome version 119.0.6045.200 (Official Build) (64-bit) Edge 121.0.2248.1 dev (64-bit)
Database | MS SQL
Browser | Edge, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | 20130353_Nguyễn Thị Phương Nhi | Member | Đọc và phân tích tài liệu, test design, test case, thực thi các test case, logs bug cho chức năng [Tìm kiếm sản phẩm].
2
3
4
5
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan | 2023-11-28 | 2023-12-05
2 | Create test design | 2023-12-06 | 2023-12-16
3 | Create test case | 2023-12-17 | 2024-01-02
4 | Execute test and log bugs | 2024-01-03 | 2024-01-19
5 | Evaluting exit criteria & Test report | 2024-01-20 | 2024-01-24
6 | Review | 2024-01-25 | 2024-02-03
| Task | Start day from 28/11/2023 | Duration
| Create test plan | 0 | 7
| Create test design | 7 | 10
| Create test case | 17 | 16
| Execute test and log bugs | 33 | 16
| Evaluting exit criteria & Test report | 49 | 4
| Review | 53 | 9
Detail Schedule

## Detail Schedule
# | Item | Responsibilities | November |  |  | December | [48 empty] | January | [30 empty] | February
|  |  | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
1 | Tạo test plan | Team | bar: November 28
2 | Tạo test design | Team | bar: December 6
2.1 | Tìm kiếm sản phẩm | Nguyễn Thị Phương Nhi | bar: December 6
2.2 | Review | Team | bar: December 16
3 | Tạo test case | Team | bar: December 17
3.1 | Tìm kiếm sản phẩm | Nguyễn Thị Phương Nhi | bar: December 17
3.2 | Review | Team | bar: January 2
4 | Thực thi test and logs bug | Team | bar: January 3
4.1 | Tìm kiếm sản phẩm | Nguyễn Thị Phương Nhi | bar: January 3
4.2 | Review | Team | bar: January 19
5 | Đánh giá tiêu chí kết thúc và test report | Team | bar: January 20
6 | Review | Team | bar: January 25

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
No | Code | Name | Role | Mission | Evaluate | Note
1 | 20130353 | Nguyễn Thị Phương Nhi | Member | Create and Update test plan | Good
2
3
4
5